## Product Backlog
ID | Theme | As a/an | I want to… | so that… | Notes | Priority | Sprint # | Status
1 | Simulator | Player | Play a game made up of fixed-duration turns | I have only a limited time to decide what to buy and sell | This is an essential property of the game. |  | 1 | TODO
2 | Simulator | Player | Know how many turns have passed since the start of the game | I know how far into the game I am |  |  |  | TODO
3 | Simulator | Player | Have a fixed number of turns in a game | The game has a fixed duration. | We don’t want the game to go on forever… |  |  | TODO
4 | Simulator | Player | See variation between the prices of shares in the market. | Share prices do not always change at the same rate/have the same price. | This is the stock value model |  | 1 | TODO
5 | Game | Player | be able to buy shares | they can make money | This needs refinement |  | 1 | TODO
6 | Game | Player | be able to see the current price of shares | they can decide what to buy/sell |  |  | 1

## Sprint 1 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections

## Sprint 1
Sprint
Start date:-5/20/2018
End date:-5/26/2018
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player, I want to play a game made up of fixed-duration turns so that I have only a limited time to decide what to buy and sell | 1 | T1.1 | Research how to create a fixed-duration turn based game |  | 0
|  | T1.2 | Design a solution for this game |  | 0
|  | T1.3 | Create Test Cases |  | 0
|  | T1.4 | Implement the solution |  | 0
As a Player,I should able to see the option to play with multiplayer mode or default play mode | 2 | T2.1 | Storyboard a UI to should display multiple players and default players |  | 0
|  | T2.2 | Design the logic to select default play mode or multiplayer mode. |  | 0
|  | T2.3 | Create Test Cases |  | 0
|  | T2.4 | Implement the logic |  | 0
|  | T2.5 | Implement the UI |  | 0
As a Player,If I select default play mode | 3 | T3.1 | Storyboard a UI to should display default play mode with 3 players accounts |  | 0
|  | T3.2 | Design the logic to play with computer(with 3 members handle by computer) |  | 0
|  | T3.3 | Create Test Cases |  | 0
|  | T3.4 | Implement the logic |  | 0
|  | T3.5 | Implement the UI |  | 0
As a Player,If I select multi play mode | 4 | T4.1 | Storyboard a UI to display multiple player mode with another 3 players accounts |  | 0
|  | T4.2 | Design the logic to play with another minimum 3 players and maximum 5 players |  | 0
|  | T4.3 | Create Test Cases |  | 0
|  | T4.4 | Implement the logic |  | 0
|  | T4.5 | Implement the UI |  | 0
As a Player,when I entered the game I able to see the following features in player account *Current balance of all the players *Current value of each stock *Notifications from the Analyst *Historical records and Current values of share prices | 5 | T5.1 | Storyboard a UI to should display the player account |  | 0
|  | T5.2 | Design the UI with following features |  | 0
|  | T5.3 | Create Test Cases |  | 0
|  | T5.4 | Implement the logic |  | 0
|  | T5.5 | Implement the UI |  | 0
As a Player, I want to see variation between the prices of shares in the market.so that share prices do not change at the same rate/have the same price. | 6 | T6.1 | Story board a UI Graphs to display the each share prices getting change with rates and time |  | 0
|  | T6.2 | Design the UI graphs of shares |  | 0
|  | T6.3 | Create Test Cases |  | 0
|  | T6.4 | Implement the design |  | 0
As a Player, I want to be able to buy shares so that I can make money | 7 | T7.1 | Storyboard a UI to capture BUY commands |  | 0
|  | T7.2 | Design a Service to handle the incoming request |  | 0
|  | T7.3 | Create Test Cases |  | 0
|  | T7.4 | Implement the Service |  | 0
|  | T7.5 | Implement the UI |  | 0
|  | T7.6 | Connect the Service to the UI |  | 0
As a Player, I want to be able to see the current price of shares so that they can decide what to buy/sell | 8 | T8.1 | Storyboard a UI to show this information |  | 0
|  | T8.2 | Design a Service to expose this information |  | 0
|  | T8.3 | Create Test Cases
|  | T8.4 | Implement the Service
|  | T8.5 | Implement the UI
|  | T8.6 | Connect the Service to the UI
As a Player, initial value should be R.S.1000 and player can buy shares if they have enough money for buy those shares. | 9 | T9.1 | Storyboard a UI to shows the initial value R.S.1000
|  | T9.2 | Design the logic to buy shares if playes have enough money.
|  | T9.3 | Create Test Cases
|  | T9.4 | Implement the logic
|  | T9.5 | Implement the UI showing the Error message or notification If player try to buy shares without Enough money
|  | T9.6 | Implement the UI showing the Sucess message or notification If player buy shares with Enough money
As a Player,able to see when bought shares the total value should be decrease From the share amount. | 10 | T10.1 | Storyboard a UI to show the balance amount
|  | T10.2 | Design the logic to when bought shares the total value should be decrease From the share amount. Function *Total amount=previous amount-Shares price
|  | T10.3 | Create Test Cases
|  | T10.4 | Implement the logic
|  | T10.5 | Implement the UI
As a Player,I want to see my current stocks and others current stocks also can view the transaction history(record of all the stock bought/sold by the player) (The Broker Component) | 10 | T10.1 | Storyboard a UI to show the stock of all players
|  | T10.2 | Design the logic to View Current stock and transaction details of all players
|  | T10.3 | Create Test Cases
|  | T10.4 | Implement the logic
|  | T10.5 | Implement the UI
As a Player, I want to sell the shares | 11 | T11.1 | Storyboard a UI to capture sell commands
|  | T11.2 | Design a Service to handle the incoming request
|  | T11.3 | Create Test Cases
|  | T11.4 | Implement the Service
|  | T11.5 | Implement the UI
|  | T11.6 | Connect the Service to the UI
As a Player, when I sold the shares my current balance should be increase | 12 | T12.1 | Storyboard a UI to show the balance amount
|  | T12.2 | Design the logic to when sold the shares the total value should be increase Function *Total amount=previous amount+Sold share prices
|  | T12.3 | Create Test Cases
|  | T12.3 | Implement the Service
|  | T12.4 | Implement the UI